## Basic Manual Gantt Chart
Task Name | Start Date | End Date | Duration | Start Date in Number Form | 43024
Task One - Create plan for semester 1 | 2017-10-16 | 2017-10-20 | 4
Task Two - Minute meetings | 2017-10-12 | 2017-12-11 | 60
Task Three - Research into current systems | 2017-10-21 | 2017-10-28 | 7
Task Four - Identify flaws in current systems | 2017-10-29 | 2017-11-01 | 3
Task Five - Find methods to improve current systems | 2017-11-02 | 2017-11-06 | 4
Task Six - Decide basic functions and features to incorporate | 2017-11-07 | 2017-11-11 | 4
Task Seven - Create designs for prototype | 2017-11-12 | 2017-11-19 | 7
Task Eight - Additional research for interim report | 2017-11-20 | 2017-11-25 | 5
Task Nine - Write Interim report | 2017-11-26 | 2017-12-16 | 20
Task Ten - Create Prototype based upon design | 2017-11-26 | 2017-12-11 | 15
Task Eleven - Make improvements to prototype | 2017-12-12 | 2017-12-17 | 5
Task Twelve - Dissertation | 2017-12-18 | 2018-01-14 | 27
Task Thirteen | 2017-12-18 | 2017-12-31 | 13
Task Fourteen | 2017-12-18 | 2017-12-31 | 13
Task Fifteen | 2017-12-18 | 2017-12-31 | 13
Task Sixteen | 2017-12-18 | 2017-12-31 | 13
Task Seventeen | 2017-12-18 | 2017-12-31 | 13

## Gantt Chart - Manual End Date
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43024
Task One - Create plan for semester 1 | 2017-10-16 | 2017-10-20 | 4 | 2 | 2 | 50%
Task Two - Minute meetings | 2017-10-12 | 2017-12-11 | 60 | 45 | 15 | 75%
Task Three - Research into current systems | 2017-10-21 | 2017-10-28 | 7 | 1.75 | 5.25 | 25%
Task Four - Identify flaws in current systems | 2017-10-29 | 2017-11-01 | 3 | 3 | 0 | 100%
Task Five - Find methods to improve current systems | 2017-11-02 | 2017-11-06 | 4 | 3 | 1 | 75%
Task Six - Decide basic functions and features to incorporate | 2017-11-07 | 2017-11-11 | 4 | 1.4 | 2.6 | 35%
Task Seven - Create designs for prototype | 2017-11-12 | 2017-11-19 | 7 | 1.75 | 5.25 | 25%
Task Eight - Additional research for interim report | 2017-11-20 | 2017-11-25 | 5 | 3.5 | 1.5 | 70%
Task Nine - Write Interim report | 2017-11-26 | 2017-12-16 | 20 | 3 | 17 | 15%
Task Ten - Create Prototype based upon design | 2017-11-26 | 2017-12-11 | 15 | 9 | 6 | 60%
Task Eleven - Make improvements to prototype | 2017-12-12 | 2017-12-17 | 5 | 3.25 | 1.75 | 65%
Task Twelve - Dissertation | 2017-12-18 | 2018-01-14 | 27 | 6.75 | 20.25 | 25%
Task Thirteen | 2017-12-18 | 2017-12-31 | 13 | 3.9 | 9.1 | 30%
Task Fourteen | 2017-12-18 | 2017-12-31 | 13 | 6.5 | 6.5 | 50%
Task Fifteen | 2017-12-18 | 2017-12-31 | 13 | 5.2 | 7.8 | 40%
Task Sixteen | 2017-12-18 | 2017-12-31 | 13 | 4.55 | 8.45 | 35%
Task Seventeen | 2017-12-18 | 2017-12-31 | 13 | 1.95 | 11.05 | 15%

## Gantt Chart - Manual Duration
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete | Start Date in Number Form | 43024
Task One - Create plan for semester 1 | 2017-10-16 | 2017-10-20 | 4 | 2 | 2 | 50%
Task Two - Minute meetings | 2017-10-12 | 2017-12-11 | 60 | 45 | 15 | 75%
Task Three - Research into current systems | 2017-10-21 | 2017-10-28 | 7 | 1.75 | 5.25 | 25%
Task Four - Identify flaws in current systems | 2017-10-29 | 2017-11-01 | 3 | 3 | 0 | 100%
Task Five - Find methods to improve current systems | 2017-11-02 | 2017-11-06 | 4 | 3 | 1 | 75%
Task Six - Decide basic functions and features to incorporate | 2017-11-07 | 2017-11-11 | 4 | 1.4 | 2.6 | 35%
Task Seven - Create designs for prototype | 2017-11-12 | 2017-11-19 | 7 | 1.75 | 5.25 | 25%
Task Eight - Additional research for interim report | 2017-11-20 | 2017-11-25 | 5 | 3.5 | 1.5 | 70%
Task Nine - Write Interim report | 2017-11-26 | 2017-12-16 | 20 | 3 | 17 | 15%
Task Ten - Create Prototype based upon design | 2017-11-26 | 2017-12-11 | 15 | 9 | 6 | 60%
Task Eleven - Make improvements to prototype | 2017-12-12 | 2017-12-17 | 5 | 3.25 | 1.75 | 65%
Task Twelve - Dissertation | 2017-12-18 | 2018-01-14 | 27 | 6.75 | 20.25 | 25%
Task Thirteen | 2017-12-18 | 2017-12-25 | 7 | 2.1 | 4.9 | 30%
Task Fourteen | 2017-12-18 | 2017-12-25 | 7 | 3.5 | 3.5 | 50%
Task Fifteen | 2017-12-18 | 2017-12-25 | 7 | 2.8 | 4.2 | 40%
Task Sixteen | 2017-12-18 | 2017-12-25 | 7 | 2.45 | 4.55 | 35%
Task Seventeen | 2017-12-18 | 2017-12-25 | 7 | 1.05 | 5.95 | 15%